## Sheet1
Q4
| Week | Backend | Frontend | Difficulty (1-3 , 1=easy) | Release | Demo
| 2020-10-01 | Build system | Build system | 1 |  | Github/Azure environment demo
| 2020-10-08 | Set up scaffolding/starter code | Set up scaffolding/starter code | 2 | 0.2 | Demo scaffolding functioniality
| 2020-10-15 | Set up Github Actions | Set up Github Actions | 2 |  | Continuous Integration demo
| 2020-10-22 | Create API scaffold | Set up API integration | 2 | 0.4 | API connection demo
| 2020-10-29 | Set up Azure Pipelines | Set up Azure Pipelines | 3 |  | Continuous Delivery demo
| 2020-11-05 | ML Prediction verification | Create user frontend | 1 | 0.6 | Demo ML predictions
| 2020-11-12 | Integrate tests in pipeline | Integrate tests in pipeline | 2 |  | Demo Frontend functionality
| 2020-11-19 | Build Locust loadtest |  | 3 | 0.8 | Locust Loadtest demo
| 2020-11-26 | Adjust Azure Webapps based on loadtest |  | 2
| 2020-12-03 | Backend ready for QA | Frontend ready for QA | 2 | 1.0/"Gold" | Overall product demo of 1.0/Gold release
| 2020-12-10 | QA Cushion | QA Cushion
| 2020-12-17 | QA Cushion | QA Cushion |  | 1.1 | Demo of 1.1 version after QA cycles
Q4 Top 3 Quarter goals |  |  |  |  | Project Management Guidelines
1 | Implement Microservice API based on Azure |  |  |  | Demo every Monday
2 | Integrate Source control and CI/CD pipeline |  |  |  | Weekly planning after demo
3 | Determine performance baselines using loadtests |  |  |  | Consumer release every 2 weeks
Tickets represent 4 hours
Q1
| Week |  |  |  | Release | Demo
TBD
Q1 Top 3 Quarter goals |  |  |  |  | Project Management Guidelines
1 | Reimplement project using Node.JS |  |  |  | Demo every Monday
2 | Replace Azure Pipelines with Github Actions |  |  |  | Weekly planning after demo
3 | Add alternative frontends for querying API |  |  |  | Consumer release every 2 weeks
Tickets represent 4 hours
Q2
| Week |  |  |  | Release | Demo
TBD
Q2 Top 3 Quarter goals |  |  |  |  | Project Management Guidelines
1 | Create Kubernetes version |  |  |  | Demo every Monday
2 | Create usage dashboard/reports |  |  |  | Weekly planning after demo
3 | Implement auto-scaling |  |  |  | Consumer release every 2 weeks
Q3
| Week |  |  |  | Release | Demo
TBD
Q3 Top 3 Quarter goals |  |  |  |  | Project Management Guidelines
1 | Design Geo-distributed version |  |  |  | Demo every Monday
2 | Implement business contuity/disaster recovery scenarios |  |  |  | Weekly planning after demo
3 | Update API to allow 3rd party integration |  |  |  | Consumer release every 2 weeks